## Project Timeline
YOUR PROJECT
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2014-09-01 | Project Start | 15 | 1
2014-10-01 | Finish R&D Phase | 5 | 1
2014-10-01 | Start Implement Backend | -5 | 1
2014-10-20 | Finish Implement For Back End | 5 | 1
2014-10-31 | Finish Testing and Fix Bug for BE | 8 | 1
2014-11-01 | Release BE | -5 | 1
02/11/.2014 | Start Implement Front End | 5 | 1
2014-12-15 | Finish Implement For Front End | -5 | 1
2014-12-28 | Finish Testing and Fix Bug for FE | 5 | 1
2014-12-29 | Release version 0.1 | -15 | 1
2015-02-03 | Finish UAT and correct process | 5 | 1
2015-02-14 | Release version 1.0 | 15 | 1
1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.