## ToDoList
To Do List | [5 empty] | © 2014 by Vertex42.com
Project: Restaurant Insight Ver 1.0 | [5 empty] | To Do List Template
Project / Task | Status | Priority | PICK | Due Date | Owner | Notes
Phase 1.0
Module: Common
Misc
Design layout and icon | Planning |  |  |  |  | Quy Nhon side will in charge
Master Data
Table | Planning
Food category | Planning
Food | Planning
Session | Planning
Position name | Planning
Design DB | Planning |  |  | 2014-09-13
Technical Item
Apply layout | Planning |  |  | 2004-09-17
Notification | Planning
Build Control
Date time picker | Completed
Auto complete | Planning
Message box | Planning
Module: Security
Create Prototype | Completed | high
Manage User | Completed
Reset password | Completed
Create User | Completed
Login for Client Side | Completed
Login for Server Side | Completed
Design DB | Completed | high
Implement
Search user information | Completed
Assign role | Completed
Reset password for server side | Completed
Reset password for client side | Completed |  |  | 2014-09-13
Delete role | Completed
Delete user | Completed
Create User | Completed
Create role | Completed
Login for Client Side | Completed
Login for Server Side | Completed
Testing | Planning
Revise prototype to release final product | Planning
Module: Waiter
Create Prototype
Menu
Table Management
Food Information
Order of Table
Design DB
Implement
Menu
Table Management
Food Information
Order of Table
Testing
Note on D4: PICK is an acronym for: Possible (easy / low value) Implement (easy / high value) Challenge (hard / high value) Kill (hard / low value).

## Lists
Status | Priority | PICK
- | - | - | Edit these lists to change what shows up within the drop-down lists in the To Do List table.
Planning | high | Easy / Low Value
Pending Approval | normal | Easy / High Value
Approved | low | Hard / High Value
In Progress |  | Hard / Low Value
Pending Review
On Hold
Completed

## Help
HELP |  | © 2014 Vertex42.com
http://www.vertex42.com/ExcelTemplates/to-do-list-template.html
About
This to-do list was designed to be easy to customize. You can insert and delete columns as needed. To add more rows, just drag the table's drag handle in the lower right corner of the table.
Use the Lists worksheet to change what shows up in the drop-down lists in the Status, Priority, and PICK columns.
See the references below for more information about creating drop-down lists with data validation and named ranges.
Conditional Formatting
The Priority and Due Date columns use conditional formatting to highlight specific values. If you change the items in the Priority list, then you may need to edit the conditional formatting rule(s) as well.
In the ToDoList worksheet, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit the rules.
PICK
The PICK column can be used to help you indicate the Difficulty (easy or hard) and Payoff Value (low or high) for a particular task. You can delete this column if you don't want to use it.
See the PICK Chart page on Vertex42.com for more information about this method.
Terms of Use
This spreadsheet, including all worksheets and associated content is considered a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
See License Agreement
http://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this Help worksheet. If necessary, you may hide it by right-clicking on the Help tab and selecting Hide.
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.
REFERENCES
TIPS | Vertex42.com: Spreadsheet Tips Workbook
ARTICLE | Vertex42.com: PICK Chart
ARTICLE | Vertex42.com: Creating a Drop Down List via Data Validation
ARTICLE | Vertex42.com: Dynamic Named Ranges
Why this spreadsheet cannot be edited in Office for iPhone
- This worksheet uses the OFFSET function for dynamic named ranges
(work around: change the ranges to simple range references)
- Table formatting is not preserved, and you cannot edit values within Tables
(work around: convert the Tables to ranges)
- Conditional Formatting is not shown when viewing on the iPhone